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SECTION ONE
1.0 INTRODUCTION
1.1	Background of the District
The Sunyani West Municipal Assembly (SWMA), which was carved out of Sunyani East District now Sunyani Municipal, is one of the 11 districts in the now Bono Region of the Republic of Ghana. It was established in November 2007 by the Legislative Instrument (LI) 1881 and has moved from District to Municipal status under Local Government Act, 2016 (Act 93) inaugurated on November, 2019 with Odomase as the administrative capital.

1.2 Scope and Focus: Vision and Mission
The SWMA’s vision is a future in which all inhabitants will experience enhanced living conditions and adequate socio-economic services of satisfactory quality in a well-maintained, highly decentralized and democratic environment.
The mission of the Assembly is to attain high standards of living for the inhabitants of the district through public-private collaboration, provision of facilities, social services, improved farming and husbandry methods in a sustained environment, and promoting governance through the strengthening of the Municipal Assembly’s (MA) structures.
Our core values are accountability, client-oriented, creativity, diligence, equity, integrity, innovativeness, loyalty, commitment, anonymity, impartiality, permanence, timeliness and transparency. 
We also embrace the cultural and ethnic diversity of the Municipality and are committed to promoting good governance, partnership and environmentally sustainable technologies for development actions.

1.3 Objectives of the Assembly
In line with the National Medium-Term Development Policy Framework for 2019-2021, the Assembly has adopted the objectives and strategies which are relevant to the achievement of its development aspirations for implementation in its Municipal Medium Term Development Plan for 2019-2021 and Annual Action Plan for 2021.  The goals, objectives, strategies, programmes and sub-programmes are shown in the tables below. 







CHAPTER TWO

2.1 Annual Implementation Plan 
This section presents the Annual Action Plan for 2021. Specifically, it indicates the various programmes, sub-programmes and their related activities, location, expected outputs, time frame, estimated cost and implementing agencies. 
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ANNUAL ACTION PLAN FOR 2021

Development Dimension 1: Economic Development 
Goal 1: To build a prosperous society 
	Adopted Strategies
	Programme/ Sub-programmes 
	Projects/
Activities
	Location
	Baseline 
For 2019
	Output indicators

	Time Frame (Quarters)        2020
	Indicative Budget
	Implementing Agencies

	
	
	
	
	
	
	
	GoG
	IGF
	Donor
	Lead
	Colla.

	Private Sector Development
	
	
	
	
	
	
	
	
	
	
	

	3.3 Support entrepreneurs and SME development
	
	
	
	
	
	
	
	
	

	3.3.1 Create an entrepreneurial culture, especially among the youth (SDG Targets 4.4,8.3,8.6)
	Economic Development /Trade, Industry and Tourism Services 
	Support entrepreneurial skill training
	Selected project beneficiary communities 
	No. of youth enterprises established
	New trainings conducted for youth enterprises established
	1st January – 30th Sept. 2021
	30,000.00
	-
	100,000.00
	ACTIOAID/SWMA
	NIIT, NVTI

	3.4 Enhance Domestic Trade 
	
	
	
	
	
	
	
	
	

	3.4.6 Develop modern markets and retail infrastructure in every district to enhance domestic trade (SDG Targets 17.15)
	Economic Development /Trade, Industry and Tourism Services 
	Completion of lockable stores at kwatire 
	Kwatire, 
	Traders sell under grass roofed sheds and in the open
	Lockable stores completed
	1st January – 30th Sept. 2021
	25,000.00
	-
	-
	CAD
	PS

	
	
	Construction of 3No. storey building 
	Sansama, Fiapre and Chiraa
	
	
	1st January – 30th Sept. 2021
	100,000.00
	
	100,00.00
	CAD
	Dept. of Agric

	
	

	Construct animal slaughter slabs at Odomase and Chiraa
	Odomase, Chiraa
	No slaughtering slabs or slaughter house in the district
	Animal slaughter slab completed
	1st January – 30th Sept. 2021
	50,000.00
	-
	-
	CAD
	Dept. of Agric

	
	
	Conversion of kobedi market stalls into lockable stores
	kobedi
	Traders sell under grass roofed sheds and in the open
	Lockable stores completed
	1st January – 30th Sept. 2021
	30,000.00
	-
	-
	CAD
	PS

	
	
	Completion of lockable stores at Fiapre
	Fiapre
	
	Lockable stores completed
	1st January – 30th Sept. 2021
	25,000.00
	-
	-
	CAD
	Dept. of Agric

	
	
	Construction of 3-Bedroom Staff bungalow at Odomase for Agric Department
	
Odomase
	
No accommodation for the department
	3-Bedroom bungalow constucted
	1st January – 31st Dec. 2021
	240,000.00
	
	
	CAD
	Dept. of Agric

	4.2 Ensure improved public investment
	
	
	
	
	
	
	
	
	

	4.2.6 Introduce District Chamber of Agriculture, Commerce and Technology (DCACT) with the mandate to promote agribusiness through enhanced interface between private and public sectors at the district level. (SDG Target 16.6)
	Agricultural Development 
	Support to government flagship programmes (PFJ, 1DF, etc.)
	Entire Municipality 
	
	Government Flagship programmes supported 
	1st January – 31st Dec. 2021
	30,000.00
	-
	-
	Dept. of Agriculture 
	SWMA, NGOs

	4.3 Improve production efficiency and yield 
	
	
	
	
	
	
	
	
	

	4.3.3 Reinvigorate extension services (SDG Target 2.a)
	Agricultural Development 
	Train 45 new FBOs and 15 existing FBOs to support extension services
	Entire District
	
	45 new FBOs and 15 existing FBOs trained 
	1st January – 30th Sept. 2021
	3,500.00
	-
	4,000.00
	Dept. of Agriculture 
	Cooperative Unit

	
	
	Organise District Farmers day celebration
	
	
	Farmers day celebrated
	1st December, 2021
	50,000.00
	-
	
	Dept. of Agriculture 
	SWMA, 

	 
	Agricultural Development 
	Provide agriculture extension services to all farmers


	








Entire Municipality 
	
	30 extension demonstrations on relevant technologies along the value , 40 field days on demonstrations and 2 study tours conducted 
	1st January – 31st Dec. 2021
	18,000.00
	-
	18,000.00
	Dept. of Agriculture 
	SWMA, NGOs

	 
	Agricultural Development 
	
	
	
	3768  home and field visits undertaken yearly to educate farmers and other stakeholders on improved technologies 
	1st January – 31st Dec. 2021
	40,800.00
	-
	40,800.00
	Dept. of Agriculture 
	SWMA, NGOs

	 
	Agricultural Development 
	
	
	
	functional two (2) plant clinics in the district
	1st January – 31st Dec. 2021
	600.00
	-
	-
	Dept. of Agriculture 
	SWMA, NGOs

	4.3.4 Ensure effective implementation of the yield improvement programme   (SDG Targets 2.1, 2.4)
	Agricultural Development 
	Organize training for 200 crop farmers and 150 livestock/poultry farmers yearly on improved technologies and livestock husbandry practices respectively
	





Entire Municipality

	
	At least 200 individual farmers trained  yearly on improved technologies trained  & post-harvest activities
	1st January – 31st Dec. 2021
	3,200.00
	3,200.00
	-
	Dept. of Agric.
	SWMA, NGOs

	 
	Agricultural Development 
	
	
	
	At least 150 livestock/poultry farmers trained in good husbandry and  management practices and 150 farmers on animal nutrition annually
	1st January – 31st Dec. 2021
	6,000.00
	-
	6000.00
	Dept. of Agriculture 
	SWMA, NGOs

	 
	Agricultural Development 
	Introduce a sustained programme of vaccination for all livestock and poultry
	Entire Municipality
	
	Number of livestock vaccinated annually against common diseases 
	1st January – 31st Dec. 2021
	4,000.00
	-
	4,000.00
	Dept. of Agriculture 
	SWMA, NGOs

	 
	Agricultural Development 
	Carry out and disseminate agriculture statistics, research results and information on weather annually
	Entire Municipality
	
	
	1st January – 31st Dec. 2021
	10,000.00
	-
	10,000.00
	
	

	 
	Agricultural Development 
	Provide support services and logistics for the implementation of Dept. of agriculture programmes
	Municipality
	
	computers, a printer, scanner, modem and pen drives procured
	1st January – 31st Dec. 2021
	6,100.00
	-
	-
	
	

	 
	Agricultural Development 
	
	
	
	Motor bikes purchased
	1st January – 31st Dec. 2021
	14,000.00
	-
	-
	
	

	
	Agricultural Development 
	
	
	
	Internal management and organization functions undertaken
	1st January – 31st Dec. 2021
	26,400.00
	-
	26, 400.00
	 Dept. of Agriculture
	

	
	Agricultural Development 
	
	
	
	At least 486 internal monitoring and supervisory visits and 12 inter-departmental monitoring and evaluation visits  undertaken yearly 
	1st January – 31st Dec. 2021
	46,000.00
	-
	46,000.00
	Dept. of Agriculture
	

	 
	Agricultural Development 
	
	
	
	At least 3 zonal planning sessions, monthly review meetings, two technical review sessions and one district RELC planning session organized annually
	1st January – 31st Dec. 2021
	11,600.00
	-

	11,600.00
	Dept. of Agriculture 
	SWMA, FBOs

	4.4Improve Post-Harvest Management 
	
	
	
	
	
	
	
	
	

	 


	Agricultural Development 
	Organize trainings for 150 processors on the processing and storage of agriculture produce (cassava, maize and vegetables) annually
	Entire District
	None
	150 processors staple food processors trained
	1st January – 31st Dec. 2021
	6,400.00
	-
	6,400.00
	Dept. of Agriculture 
	SWMA, NGOs

	4.4.6. Facilitate the provision of storage infrastructure with a drying system at the district level and a warehouse receipt system (SDG Targets 2.3, 12.1,12.3.12.a)
	Agricultural Development
	Complete payment for  construction of warehouses for maize markets at Nsoatre
	Nsoatre
	
	Warehouse constructed 
	1st January – 31st December  2021
	200,000.00
	-
	-
	Dept. of Agriculture 
	SWMA, 







	6.1.4 Promote and enforce local tourism and develop available and potential sites to meet internationally acceptable standards (SDG Targets 8.9)
	Tourism Development
	Identify and document tourism potential
	Entire District
	
	Tourism potentials identified
	1st January – 31st Dec. 2021
	2,000.00
	
	
	Centre for National Culture
	CAD

	
	
	TOTAL= 18
	
	
	
	

	
	
	
	
	





Development Dimension 2: Social Development 
Goal 2: To create opportunities for all
	
	
	
	
	
	
	
	Indicative Budget
	Implementing Agencies

	Adopted Strategies
	Programme/ Sub-programmes 
	Projects/
Activities
	Location
	Baseline for 2019
	Output indicators
	Time Frame
	GoG
	IGF
	Donor
	Lead
	Colla.

	1.1 Enhance inclusive and equitable access to, and participation in quality education at all levels 
	
	
	
	
	
	
	
	
	

	1.1.5 Ensure inclusive education for all boys and girls with special needs (SDG Targets 4.1, 4.2, 4.5, 4.a)

	Social Services Delivery
	Organize sensitization workshops for parents to send their children with special needs to school 
	Entire Municipality
	Identified children with special needs integrated in the education system
	Identified children with special needs integrated in the education system
	1st January – 31st Dec. 2021
	4,000.00
	-
	-
	GES

	GHS, DSWDC

	
	Social Service Delivery /Education and Youth Development
	Provide financial assistance to 50 needy but brilliant boys and girls at post basic educational institutions (vocational/technical, secondary etc.)
	Odomase
	
	50 needy but brilliant students provided with financial support
	1st January – 31st Dec. 2021
	50,000.00
	-
	-
	GES

	SWMA

	
	
	Support Municipal Education Fund 
	Entire Municipal 
	
	Municipal Education Fund
	1st January – 31st Dec. 2021
	75,741.10
	-
	-
	GES

	SWMA

	1.1.6 Popularize and demystify the teaching and learning of science, technology, engineering and mathematics (STEM) and ICT education in basic and secondary education. (SDG Target 4.1)
	Education and Youth Development
	Organize science, technology, engineering  and mathematics (STEM) and ICT Education clinics annually 
	Odomase
	
	Number of boys and girls participated in STEM and ICT
	1st January – 31st Dec. 2021
	9,000.00
	-
	-
	GES

	SWMA

	
	
	Providing desktop computers for schools
	Entire Municipality
	
	Providing desktop computers for schools completed 
	1st January – 31st Dec. 2021
	100,000.00
	-
	-
	SWDA
	GES

	
	
	Complete payment for Construction of 1No. 3-unit classroom block with ancillary facilities at Abronye Presby Primary 
	Abronye 
	
	1No. 3-unit classroom block with ancillary facilities at Abronye Presby School constructed 
	1st January – 31st Dec. 2021
	10,,472.30
	
	
	SWDA
	GES

	
	
	Construction of 1No. 3-unit KG Block for Notre Dame Girls Model School
	Fiapre
	
	1No. 3-unit KG Block for Notre Dame Girls Model School constructed 
	1st January – 31st Dec. 2021
	250,000.00
	
	
	SWDA
	GES

	1.1.10 Expand infrastructure and facilities at all levels (SDG Target 4.a)
	Education and Youth Development
	Construction of workshop for Nsoatre Vocational Institute
	Nsoatre
	
	Workshop contsructed
	1st January – 31st Dec. 2021
	-
	-
	
	GES
	SWMA

	
	
	Renovation of school buildings
	Municipal wide
	
	
	1st January – 31st Dec. 2021
	
	
	
	GES
	SWMA

	

	
	Construction of 1No. 6-Bedroom Teacher’s Bungalow 
	Adouonya
	
	
	1st January – 31st Dec. 2021
	340,000.00
	-
	.
	GES
	SWMA

	

	
	Procurement of 400 PCS Dual Desk for Schools 
	Municipal Wide 
	
	
	1st January – 31st Dec. 2021
	120,00.00
	-
	.
	GES
	SWMA

	
	
	Complete payment for construction of 1No.3Units-Classroom block with Ancillary Facilities at Mantukwa 
	Mantukwa 
	
	payment for construction of 1No.3Units-Classroom block with Ancillary Facilities at Mantukwa completed 
	1st January – 31st Dec. 2021
	14,872.45
	-
	-
	GES
	SWMA

	 
	Education and Youth Development
	Rehabilitate basic schools with dilapidate classroom infrastructure
	Chiraa/Nsoatre/ Odomase
	
	Selected schools
	1st January – 31st Dec. 2021
	205,360.95
	-
	-
	GES

	SWMA

	
	
	Construction of 1No. 3-unit classroom block with ancillary facilities at African Faith Nsoatre
	Nsoatre
	
	Teaching and learning enhanced
	1st January – 31st Dec. 2021
	250,000.00
	-
	-
	GES

	SWMA

	
	
	Construction of 1No. 3-unit classroom block with ancillary facilities at Baamu
	Baamu
	
	Teaching and learning enhanced
	1st January – 31st Dec. 2021
	250,000.00
	-
	-
	GES

	SWMA

	
	
	Construct 1No. 3-unit classroom block with office, store and library for Kantro R/C Block
	Kantro
	
	1No. 3-unit classroom block with office, store and library constructed
	1st January – 31st Dec. 2021
	-
	-
	400,000.00
	GES
	SWMA

	
	
	Construction of I No. 5-seater toilet for Methodist Primary school 
	Ayakomaso
	
	Toilet Facility Constructed 
	1st January – 31st Dec. 2021
	45,000.00
	-
	-
	GES

	SWMA

	
	
	Construction of 1No. 3-unit classroom block with ancillary facilities at Fiapre Islamic 
	Fiapre 
	
	1No. 3-unit classroom block with ancillary facilities at Fiapre Islamic constructed 
	1st January – 31st Dec. 2021
	320,000.00
	-
	-
	GES

	SWMA

	
	
	Supply of furniture to Fiapre Islamic School
	Fiapre 
	
	Supply of furniture to Fiapre Islamic School completed 
	1st January – 31st Dec. 2021
	195,153.00
	-
	-
	GES

	SWMA

	1.2.2 Build effective partnership with religious bodies, civic organizations and private sector in delivery of quality education (SDG Target 17.17)
	
	Organize DEOC meetings 
	Odomase
	
	DEOC meetings held
	1st January – 31st Dec. 2021
	1,260.00
	-
	-
	GES

	SWMA

	1.2.7 Enhance quality teaching and learning (SDG Targets 4.7, 4.c,)
	
	Conduct regular monitoring and supervision of schools 
	Entire Municipality
	
	All basic and secondary schools monitored
	1st January – 31st Dec. 2021
	5,247.00

	-
	-
	GES

	CAD, SWCD

	1.2.8 Ensure adequate supply of teaching and learning materials (SDG Target 4.c)
	
	Provide teaching and learning materials for basic schools
	Selected Schools
	
	TLMs supplied
	1st January – 31st Dec. 2021
	10,050.00
	-
	-
	GES

	SWMA

	 
	Education and Youth Development
	Organize independence  Day anniversary 
	Odomase
	
	No. of schools participated in the district celebration
	1st January to 31st March 2021
	30,000.00
	-
	-
	DA
	DE

	
	
	Complete the Construction of 1No. 3-unit Teachers Bungalow  at Abisu
	Abisu
	
	Teachers Bungalow completed
	29th October, 2018 – 30th April, 2021 
	121,944.50
	
	
	GES
	SWMA

	
	
	Construction of teachers Bungalow at Adounya
	Adounya
	
	Teachers Bungalow constructed
	1st January – 31st Dec. 2021

	121,944.50
	
	
	GES
	SWMA

	1.2 Strengthen school management systems
	
	
	
	
	
	
	
	
	

	Health and Health Services
	
	
	
	
	
	
	
	
	
	
	

	2.1 Ensure affordable, equitable, easily accessible and universal health coverage
	
	
	
	
	
	
	
	
	

	


	Health Delivery

	Construction of CHPS Compound 
	Fiapre Zongo
	
	CHPS Compound constructed 
	1st January – 31st March  2021
	-
	-
	180,000.00
	GHS
	SWMA

	
	
	
	
	
	
	
	
	
	
	
	

	2.1.1 Accelerate implementation of Community based Health Planning and Services (CHPS) policy to ensure equity in access to health care (SDG Targets 1.2, 1.3, 3.1, 3.2, 3.3, 3.8, 16.6)

	Health Delivery

	Construct 1No. toilet facility for Kantro CHPS  compound with nurses quarters 
	Kantro
	
	Toilet and  nurses quarters completed
	1st January – 31st March  2021
	-
	-
	230,000.00
	GHS
	SWMA, Heart for Children’s Foundation

	2.1.2 Expand and equip health facilities (SDG Targets 3.8)
	Health Delivery
	Rehabilitate and construct additional rooms for Dumasua Health Centre
	Dumasua
	
	Additional rooms  -dispensary and laboratory provided
	1st January – 30th December 2021
	45,000.00
	-
	-
	GHS

	SWMA

	
	
	Complete payment for Construction of  fence wall and concrete walkway at Fiapre Health Centre
	Fiapre 
	
	Fence wall constructed and pavement constructed
	1st January – 30th December 2021
	100,000.00
	-
	-
	GHS

	SWMA

	
	
	Support the construction of NHIS office 
	Odomase 
	
	NHIS office constructed 
	1st January – 30th December 2021
	6,266.66
	-
	-
	GHS

	SWMA

	
	
	Furnishing of Health Facilities within the Municipal 
	Municipal Wide 
	
	Health Facilities within the Municipal furnished 
	1st January – 30th December 2021
	100,000.00
	-
	-
	SWMA
	GHS

	2.3.2 Intensify implementation of malaria control programme (SDG Target 3.3)

	Health Delivery
	Support malaria prevention education and services
	Entire Municipality
	Not applicable
	Number of participants educated by gender
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	GHS

	SWMA

	2.4 Ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups
	
	
	
	
	
	
	
	
	

	HIV & AIDS
	
	
	
	
	
	
	
	
	
	
	

	2.4.3 Intensify behavior change strategies, especially for high-risk groups for HIV and AIDS and TBs (SDG Targets 3.3, 3.7)
	Health Delivery
	Implement District Response activities on HIV & AIDS
	Entire Municipality
	
	Number of HIV counselling and testing services conducted
	1st January – 31st Dec. 2021
	7,862.44
	-
	-
	GHS

	SWMA

	Population Management
	
	
	
	
	
	
	
	
	
	
	

	4.1.7 Improve maternal and adolescent reproductive health  (SDG Targets 3.1, 3.7) 
	
	Support Ghana Health Service to deliver adolescent health services
	All Adolescent Corners
	
	Increased number of adolescents accessing services from adolescent corners 
	1st January – 31st Dec. 2021
	2,500.00
	-
	-
	GHS

	SWMA

	
	
	
	
	
	
	
	
	
	
	
	

	Water & Sanitation 
	
	
	
	
	
	
	
	
	
	
	

	5.1 Improve access to safe and reliable water supply services for all
	
	
	
	
	
	
	
	
	

	5.1.7 Undertake 
tree planting along the banks of all major water bodies and their tributaries to reduce silting and pollution from human activities
	Water bodies management 
	Support CBO initiated tree planting campaigns along major river bodies and around school buildings 
	Selected communities
	
	Trees planted along major river bodies and school buildings
	1st January – 31st Dec. 2021
	1,500.00
	-
	-
	Forest Services Division
	SWMA, NADMO, CBOs

	 5.1.2 Ensure sustainable financing of operations and maintenance of water supply systems (SDG Target 17.3)

	Water and Sanitation
	Maintenance of existing boreholes 
	Entire Municipality 
	
	Broken down boreholes maintained 
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	MWD/DWST
	CWSA

	5.1.3 Provide mechanized borehole and small town water systems (SDG Target 6.1)
	Water and Sanitation
	Support community mobilization and drilling/construction of 20 potable water systems (boreholes fitted with pumps and piped systems)
	Entire Municipality
	
	Supported the construction of 20 boreholes with hand pumps
	1st January – 31st Dec. 2020
	38,250.00
	-
	- 
	MWD/DWST
	CWSA

	
	
	Construction and drilling of 8No. boreholes with fitted hand pumps
	Notre Dame shs
Chiraa–Oti Yeboah 
Canada
SAHES
Kantro No.1
Boliso –Nsoatre
Beposo-Abisu
Afrasu No.2
	
	Construction and drilling of 8No. boreholes with fitted hand pumps completed 
	1st January – 31st Dec. 2021
	100,000.00
	-
	-
	MWD/DWST
	CAD

	
	
	Drilling of 3No. Boreholes  and Mechanization of 1 existing borehole with hand pump 
	Kessabente 
Timbernkwanta , Aduonya 
Apprakukrom 
	
	3No. Boreholes  and of 1 existing borehole with hand pump drilled and maintained 
	1st January – 31st Dec. 2020
	30/567.77
	-
	-
	MWD/DWST
	CWSA

	
	
	Drilling and Construction of 10No. Boreholes with Hand Pump
	Abisu
Nkranketewaa 
Kantro No.2 
Kantro No.2
Yawsankro 
Fawoman 
Appiakrom
Nsamsam City 
Attakrom 
Tailokrom 
	
	Drilling and Construction of 10No. Boreholes with Hand Pump completed 
	1st January – 31st Dec. 2020
	257,000.00
	-
	-
	MWD/DWST
	CWSA

	Social Services Delivery
	Water and Sanitation
	Rehabilitate 20 potable water supply systems 
	Entire Municipality
	
	20 water facilities rehabilitated 
	1st January – 31st Dec. 2020
	108,000.00
	-
	-
	MWD/DWST
	Area Mechanics, Contractors 

	
	
	Support the operations of the MWST
	Entire District
	
	Regular monitoring of water facilities
	1st January – 31st Dec. 2020
	10,000.00
	-
	-
	MWD/MWST
	CAD

	Environmental Sanitation and Hygiene
	
	
	
	
	
	
	
	
	
	
	

	5.2 Enhance  access to improved and reliable environmental sanitation services
	
	
	
	
	
	
	
	
	

	 5.2.2 Create space for private sector participation in the provision of sanitation services (SDG Target 17.17)

	Environmental Health and Sanitation Management
	Partner private sector companies/individuals to provide modern public toilets in major towns 
	Odomase, Nsoatre, Chiraa, Dumasua and Fiapre,
	
	Improved sanitation services and clean environment 
	1st January – 31st Dec. 2021
	55,000.00
	-
	-
	CAD-MEHSU
	Private Sector Investors, SWMA

	 5.2.4 Promote National Total Sanitation Campaign (SDG Target 6.2)

	Environmental Health and Sanitation Management
	Conduct  environmental sensitization campaigns 
	Entire Municipality
	
	Number of communities sensitized 
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	MEHSU
	ISD

	
	Environmental Health and Sanitation Management
	Evacuate/level refuse heaps in major settlements 
	Chiraa, Nsoatre Fiapre and Odomase 
	
	Refuse heaps evacuated
	1st January – 31st Dec. 2021
	100,000.00
	-
	-
	CAD-EHSU
	Private Sector Organization

	 
	Environmental Health and Sanitation Management
	Procure sanitation tools and facilities for cleaning and general services
	Entire Municipality
	
	Brooms, detergents, rakes, litter bins supplied
	1st January – 31st Dec. 2021
	100,000.00
	-
	
	EHSU
	CAD

	
	
	Construction of 1No. 2-seater toilet and urinal at Fiapre Durbar Grounds
	Fiapre
	
	Toilet and Urinal completed
	1st January – 31st Dec. 2021
	20,000.00
	-
	
	EHSU
	CAD

	Poverty and inequality 
	
	
	
	
	
	
	
	
	
	
	

	6.1.Eradicate poverty in all its forms and dimension 
	
	
	
	
	
	
	
	
	

	6.1 Empower the vulnerable to access basic necessities of life (SDG Target 1.4)
	Social Services Delivery
	Organize sensitization campaigns on social issues for vulnerable groups
	Entire Municipality
	
	Knowledge impacted
	1st January – 31st Dec. 2021
	1,000.00
	-
	-
	MSCD
	UTAC, TAs, CBOs

	Child and Family Welfare
	
	
	
	
	
	
	
	
	
	
	

	7.1 Ensure effective child protection and family welfare system 
	
	
	
	
	
	
	
	
	

	7.1.10 Increase awareness on child protection laws and policies (SDG Targets 5.3, 16.2, 16.3)
	Social Welfare and Community Development 
	Educate the public and enforce child protection laws and policies
	Entire Municipality
	Number of education campaigns organized 

Number of cases resolved 
	
Public educated on child protection laws
	1st January – 31st Dec. 2021
	300.00
	-
	-
	MSWCD
	SWMA, UTACs

	7.2.2 Enhance inclusion of children with disability and special needs in all spheres of child development  (SDG Targets 4.5, 4.a, 10.2, 11.2)

	
	Identify, register and link children with disability and special needs to the relevant institutions for integration or support
	Entire Municipality
	
	Disabled children identified and supported
	1st January – 31st Dec. 2021
	600.00
	-
	-
	MSWCD
	CAD, DOVVSU, CHRAJ

	
	
	Undertake Gender based activities 
	Entire Municipality
	
	
	
	
	
	
	
	

	7.2.6 Eliminate the worst forms of child labour by enforcing laws on child labour and child protection (SDG Targets 5.3, 16.2, 16.3)
	
	Support the establishment of relevant structures (child panels etc.) to promote justice for children, 
	Entire Municipality
	
	Relevant child protection structures established
	1st January – 31st Dec. 2021
	100.00
	-
	-
	MSWCD
	CAD, DOVVSU, CHRAJ

	Gender Equality
	
	
	
	
	
	
	
	
	
	
	

	9.2 Promote economic empowerment of women
	
	
	
	
	
	
	
	
	

	9.2.5 Improve access to education, health and skills training in income generating activities for vulnerable persons including head potters (SDG Targets 3.8, 4.5)
	Social Welfare and Community Development 
	Support the organization of skills training for target groups and unemployed women 
	Entire Municipality
	
	Skills training organised for target and unemployed women groups
	1st January – 31st Dec. 2021
	1,000.00
	-
	-
	MSWCD
	SWMA, UTACs

	
	
	Organize adult education programmes/mass meetings on issues affecting children and domestic violence. 
	Entire Municipality
	
	72 groups trained on child related issues and domestic violence 
	1st January – 31st Dec. 2021
	300.00
	-
	-
	MSWCD
	CAD, DOVVSU, CHRAJ

	Social Protection
	
	
	
	
	
	
	
	
	
	
	

	10.1 Strengthen social protection especially for children women persons with disabilities and the elderly
	
	
	
	
	
	
	
	
	

	10.1.3 Strengthen and effectively implement existing social protection intervention programmes and expand their coverage to include all vulnerable groups (SDG Targets 1.3, 5.4, 10.4)
	Social Welfare and Community Development 
	Support the implementation of livelihood Empowerment Against Poverty Programme 
	Entire Municipality
	
	Number of beneficiaries 
	1st January – 31st Dec. 2021
	1000.00
	-
	-
	MSWCD
	CAD

	 Social Services Delivery
	Social Welfare and Community Development 
	Conduct inspection visits to early childhood development centres 
	Odomase, Fiapre Nsoatre, Chiraa circuits
	
	12 public and private early childhood development centres inspected
	1st January – 31st Dec. 2021
	340.00
	-
	-
	MSWCD
	CAD

	Social Services Delivery
	Social Welfare and Community Development 
	Mediate and provide counselling on child and family welfare conflicts/issues to clients
	Odomase
	
	Type and Number of conflicts resolved 
	1st January – 31st Dec. 2021
	300.00
	-
	-
	MSWCD
	CAD

	Gender Equality
	
	
	
	
	
	
	
	
	
	
	

	Social Services Delivery
	Social Welfare and Community Development 
	Organize livelihood skills training for women 
	Odomase, Dumasua, Koduakrom Chiraa, Fiapre and Nsoatre 
	
	20 women groups provided with livelihood skills  
	1st January – 31st Dec. 2021
	-
	-
	-
	DSWCD
	CAD

	Disability and Development
	
	
	
	
	
	
	
	
	
	
	

	11.1 Promote full participation of PWDs in social and economic development of the country 
	
	
	
	
	
	
	
	
	

	11.1.5 Ensure effective implementation of the three (3) percent increase in DACF disbursements to PWDs (SDG Targets 16.6)
	
	Facilitate and Manage the disbursement of Disability fund
	Entire Municipality
	
	Implement PWD action plan 
Enhanced economic and social wellbeing of PWDs
	1st January – 31st Dec. 2021
	64,787.00
	-
	-
	SWMA
	PWDs,

	11.3.1 Ensure the implementation of Ghana Accessibility standards to ensure access of PWDs to the built environment, goods, services and assistive devices (SDG Targets 10.2, 11.1) 
	Social Welfare and Community Development 
	Facilitate the provision of walkways in newly constructed public buildings   
	Entire Municipality
	
	80 percent of activities implemented
	1st January – 31st Dec. 2021
	-
	500.00
	-
	SWMA
	Association of PWDs

	14.1.8 Promote less recognized sporting activities (SDG 1.a, 17.3)

	Social Services Delivery

	Support sporting activities (e.g. table tennis and football) for basic schools and communities
	Entire Municipality
	
	Sports enhanced 
	1st January – 30th June 2021
	5,000
	
	
	SWMA
	YEA

	
	
	[bookmark: _GoBack]TOTAL=61
	
	
	
	
	
	
	
	
	







Development Dimension 3: Environment, Infrastructure and Human Settlement 
Goal 3: Safeguard the natural environment and ensure a resilient built environment 
	
	
	
	
	
	
	Time Frame (Quarters)
	Indicative Budget
	Implementing Agencies

	Programmes
	Sub-programmes 
	Projects/
Activities
	Location 
	Baseline for 2017
	Output indicators
	
	GoG
	IGF
	Donor
	Lead
	Colla.

	Protected Areas
	
	
	
	
	
	
	
	
	
	
	

	1.2 Protect forest reserves 
	
	
	
	
	
	
	
	
	

	1.2.1 Support the protection of the remaining network of natural forest and biodiversity hotspots in the country (SDG Targets 6.6, 11.4, 12.2, 15.1, 15.5, 15.9, 15.a, 16.b)
	Natural Resources Conservation 
	Establish checkpoints to control illegal lumbering in forest reserves and government  plantations
	Entire Municipal 
	None 
	Check points to control illegal logging of lumber established
	1st January – 30th June 2021
	-
	2,000.00
	-
	CAD
	PS

	Climate variability and change
	
	
	
	
	
	
	
	
	
	
	

	7.1 Enhance climate change and resilience 
	
	
	
	
	
	
	
	
	

	7.1.10 Mainstream climate change in national development planning and budgeting processes (SDG Targets 11.b, 13.2)
	Environmental and Sanitation Management
	Implement climate change related risk reduction, mitigation and adaptation actions
	Entire Municipal
	
	 climate change related risk reduction, mitigation and adaptation actions implemented
	1st January – 31st December 2021
	20,000.00
	-
	-
	NADMO

	EPA, GMeT

	
	
	
	
	
	
	
	
	
	
	
	

	Disaster Management 
	
	
	
	
	
	
	
	
	
	
	

	8.1 Promote proactive planning for disaster prevention and mitigation 
	
	
	
	
	
	
	
	
	

	
	
	Planting of trees in  communities affected by sand wining  activities  
	Chiraa Ahyiamu,
Tanonom, 
Canada 
	
	Planting of trees in  communities affected by sand wining activities  implemented 
	1st January – 31st December 2020
	15,000.00
	-
	-
	NADMO

	SWDA-CAD

	8.1.1 Educate public and private institutions on natural and man-made hazards and disaster risks 
(SDG Targets 3.d, 13.3.)
	Disaster Prevention and Management
	Organize education campaigns on bushfires and associated loss of property and  danger to the environment 
	Entire Municipal
	Number of communities visited
	Number of communities educated
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	NADMO

	SWMA-CAD

	8.1.2 Strengthen early warning and response mechanism on disasters (SDG Targets 3.d, 13.3.)
	Disaster Prevention and Management
	Undertake regular removal of silt and refuse from storm drains and culverts
	Entire Municipal
	Number of communities benefitted from the exercise
	Silt removed from storm drains and gutters
	1st January – 31st Dec. 2021
	25,000.00
	-.;’
	-
	NADMO
	CAD, GNFS

	 
	Disaster Prevention and Management
	Provide relief items to disaster victims 
	Entire Municipal
	No. of relief items distributed
	Number of relief items distributed 
	1st January – 31st Dec. 2010
	20,000.00
	-
	-
	NADMO
	CAD, GNFS

	Transport Infrastructure –Road
	
	
	
	
	
	
	
	
	
	
	

	8.1Improve efficiency and effectiveness of road transport infrastructure and services
	
	
	
	
	
	
	
	
	

	 8.1.2 Expand and maintain the national road network (SDG Target 9.1, 11.2)

	Infrastructure Development
	Re-shaping and maintenance of access roads 
	Entire Municipal
	Access roads undergo routine maintenance  
	3No. culverts constructed and approaches filled. 
	1st January – 31st Dec. 2021
	-
	-
	150,000.00
	DFR
	SWMA

	
	
	
	
	
	
	
	
	
	
	
	

	Information Communication Technology
	
	
	
	
	
	
	
	
	
	
	

	10.1 Enhance application of ICT in national development 
	
	
	
	
	
	
	
	
	

	10.1.2 Mainstream ICT in public sector operations (SDG Target 17.8)

	
	Reactivate website and social media platforms


	Odmase
	Internet connection available
	Website reactivated
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	SWMA
	MTN

	Energy and Petroleum 
	
	
	
	
	
	
	
	
	
	
	

	12.2 Ensure efficient transmission and distribution system 
	
	
	
	
	
	
	
	
	

	12.2.4 Revise self-help –electricity project and use means-testing approaches to enable the poor to connect to the national grid (SDG Target 7.b)
	
	Support the extension of  electricity to unserved areas, street light and purchase of light poles   
	Entire Municipal
	Increased access to electricity in the district
	Electricity extended to unserved areas of the district
	1st January – 31st Dec. 2021
	75,000.00
	-
	-
	SWMA
	VRA, TAs, UTAC

	
	
	Extension of electricity to Health Centres 
	Entire Municipal
	Connect all Health centres to electricity 
	Extension of electricity to Health Centres completed 
	1st January – 31st Dec. 2021
	500,000.00
	-
	-
	SWMA
	VRA, TAs, UTAC

	13.Drainage and flood control
	
	
	
	
	
	
	
	
	
	
	

	13.1 Address recurrent devastating floods
	
	
	
	
	
	
	
	
	

	13.1.3 Intensify public education on indiscriminate disposal of waste (SDG Target 11.6)
	
	Organize regular campaigns for cleaning and removal of silt and waste from drains 
	Entire District
	Reduction of floods in major towns
	Campaigns for clearing and silt removal organised
	1st January – 31st Dec. 2021
	11,000.00
	
	
	NADMO
	SWMA

	14. Infrastructure maintenance
	
	
	
	
	
	
	
	
	
	
	

	14.1.3 Establish timely and effective preventive maintenance plan for all public infrastructure (SDG Target 9.a)
	
	Rehabilitate /Maintain, Refurbish and Upgrade public infrastructure
	Nsoatre, Chiraa and Dumasua 
	-
	No. of streetlights, classroom blocks, health facilities, court buildings maintained
	1st January – 31st Dec. 2021
	150,000.00
	-
	-
	SWMA
	VRA, UTAC

	Human Settlement and Housing 
	
	
	
	
	
	
	
	
	
	
	

	17.1 Promote sustainable, spatially integrated, balanced and orderly development of human settlements
	
	
	
	
	
	
	
	
	

	17.1.1 Fully implement Land Use and Spatial Planning Act 2016 (Act 925) (SDG Targets 16.6, 17.16)
	Physical and Spatial Planning 
	Organize quarterly spatial planning and technical committee meetings 
	Odomase 
	Five (5) physical planning meeting organized 
	Six (6) statutory planning and technical committee meetings held, Number of development applications approved
	1st January – 31st Dec. 2021
	-
	5,000.00

	-
	DPP
	TAs, Other government 

	Infrastructure delivery and management 
	Physical and Spatial Planning 
	Organize physical planning education for stakeholders 
	Entire District
	Five (5) physical planning education campaigns organized for stakeholders
	10 communities sensitized on physical planning procedures
	1st January – 31st Dec. 2021
	-
	8,500.00
	-
	DPP
	TAs, Other government 

	Infrastructure delivery and management 
	Physical and Spatial Planning 
	Provide technical support services to TAs
	
	
	Improved service delivery
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	DPP
	TAs, Other Government Agencies

	
	
	Procure office machines, materials and equipment for administrative and field work
	Odomase
	
	Procure office machines (two computers, A3 scanner, printer and two GPS), planning materials (satellite images etc) and field equipment (two motorbikes)
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	CAD
	SWMA

	Urban Development 
	
	
	
	
	
	
	
	
	
	
	

	19.1 Promote resilient urban development 
	
	
	
	
	
	
	
	
	

	19.1.8 Support implementation of the National Urban Policy and Action Plan and the United Nation’s New Urban Agenda adopted at Habitat III (SDG Targets 11.3,11.a, 11.b)
	“
	Support the implementation of street naming and property addressing exercises/Ghana Post digital addressing system
	Odomase and Fiapre
	Five (5) streets named and all properties address  
	Five (5) streets named and all properties address  
	1st January – 31st Dec. 2021
	50,000.00
	-
	-
	DPP
	TAs, Other government 

	
	
	TOTAL=16
	
	
	
	
	
	
	
	
	




Development Dimension 4: Governance, Corruption and Public Accountability 
Goal 4: To maintain a stable, united and safe society
		
	
	
	
	
	
	
	Indicative Budget
	Implementing Agencies

	Programmes
	Programme /Sub-programmes 
	Projects/
Activities
	Location 
	Baseline for 2019
	Output indicators
	Time Frame
	GoG
	IGF
	Donor
	Lead
	Colla.

	2.1 Deepen political and administrative decentralization 
	
	
	
	
	
	
	
	
	

	2.1.4 Institute mechanism for effective inter-service/inter-sectoral collaboration and cooperation at district, regional and national levels (SDG Targets 16.6, 16.7)
	Management and Administration
/General Administration
	Organize statutory political meetings
	Odomase
	Three GA ordinary, executive and sub-committee meetings held
	Three GA Ordinary meetings, executive committee and sub-committee meetings organized
	1st January – 31st Dec. 2021
	-
	25,000.00
	-
	MA
	Government Agencies

	
	
	Organize statutory management meetings
	Odomase
	
	At least four management meetings organized
	1st January – 31st Dec. 2021
	-
	1,500.00
	-
	CAD
	Depts of the Assembly

	
	
	Undertake landscaping, paving and construction of summer hut for DCE’s residence 
	Odomase
	
	Landscaping completed
	1st January – 31st Dec. 2021
	-
	71,324.24
	-
	SWMA
	PSO

	
	
	Furnishing of Assembly Block 
	Odomase 
	
	Furnishing of Assembly Block completed 
	1st January – 31st Dec. 2021
	50,000.0
	-
	-
	CAD
	SWMA

	
	
	Rehabilitation of DCE’s residence
	Odomase
	
	Roofing changed
	1st January – 31st Dec. 2021
	-
	85,000.00
	-
	CAD
	SWMA

	
	
	Complete payment for construction of 1N0.3-Units Semi-ditch staff quarters at Odomase 
	Odomase
	
	payment for construction of 1N0.3-Units Semi-ditch staff quarters at Odomase completed 
	1st January – 31st Dec. 2021
	32,039.22
	-
	-
	CAD
	SWMA

	2.1.5 Strengthen the capacity of the ILGS to deliver on its mandates
	
	Organize training for Assembly members and staff on the LGA
	Odomase
	None
	54 Assembly members and 24 staff trained
	1st April – 31st Dec. 2021
	20,000.00
	-
	30,000.00
	CAD
	Consultants

	2.1.7 Strengthen sub-district structures (SDG Targets 16.6, 17.9)
	General Administration
	Complete the Construction of  an office building for Fiapre Town council 
	Fiapre
	None
	Fiapre  town council office completed
	1st January – 31st Dec. 2021
	158,576.50
	-
	-
	CAD
	PS

	
	
	Provide temporary offices for Koduakrom and Dumasua Area Councils
	Koduakrom and Dumasua
	
	Temporary offices provided
	1st January – 31st Dec. 2021
	11,449.78
	-
	-
	CAD
	SWMA

	
	
	Procurement of 2No.Motobycycles for official duties 
	Odomase 
	
	2No.Motobycycles for official duties procured 
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	CAD
	SWMA

	
	
	Support the establishment of sub-structures within the Municipality 
	Entire Municipal 
	
	sub-structures established 
	1st January – 31st Dec. 2021
	75,741.00
	-
	-
	CAD
	SWMA

	
	
	Provide support services and logistics to the urban/town/area councils 
	Awua –Domase, Odomase No.1, Fiapre, Nsoatre, Koduakrom and Chiraa
	None 
	Office furniture, stationery etc
	1st January – 31st Dec. 2021
	60,000.00
	-
	-
	CAD
	Private Sector

	
	
	Complete payment for construction of District Police Station 
	Odomase 



	
	District Police Station constructed 
	1st January – 31st Dec. 2021
	17,726.16
	-
	-
	CAD
	SWMA

	
	
	Organize refresher training for 28 unit committees on their mandate and functions 
	Selected electoral areas
	None
	28 unit committees trained
	1st January – 31st Dec. 2021
	1,860.00
	-
	-
	DSWCD
	NGOs, Urban/Town/Area Council

	2.2 Improve decentralized planning through Municipal enumeration
	
	Undertake the creation of administrative database
	Entire Municipality
	-
	Administrative database created
	1st January – 31st December 2021
	
2,400.00
	-
	-
	STATS 
	All Departments

	
	
	Undertake monthly market readings on selected items for the various markets
	Entire Municipality
	-
	Computation of Monthly CPI and inflation rates
	1st January – 31st December 2021
	2,400.00
	
	
	STATS
	
GSS

	2.2.1 Strengthen local level capacity for participatory planning and budgeting (SDG Targets 16.6, 16.7.)

	Planning, Budgeting and Coordination
	Coordinate planning and budgeting activities of the Assembly
	Odomase
	Four quarterly DPCU meetings organized
	Four (4) DPCU meetings organized 
	1st January – 31st Dec. 2021
	6,000.00
	-
	-
	CAD
	SWMA

	
	
	Organization of Audit Committee meetings 
	Odomase 
	
	Four (4) Audit committee meeting organized 
	1st January – 31st Dec. 2021
	10,000.00
	-
	-
	CAD
	SWMA

	
	
	Conduct AAP implementation monitoring and evaluation.
	Odomase 
	Jointly organized with DPCU meetings
	Four (4) quarterly review meetings jointly organized with DPCU meetings
	1st January – 31st Dec. 2021
	2,000.00
	
	-
	CAD
	Depts. of the Assembly

	
	
	Organize refresher training for staff of DA and Area Council members
	Odomase 
	None
	Two refresher training organized for heads of department  of the Assembly
	1st April – 30th June 2021
	10,000.00
	
	-
	CAD
	Urban/Town/Area Councils

	2.2.4 Ensure implementation of planning and budgeting provisions in LI 2232 and the Public Financial Management Act, 2016 (Act 921) (SDG Targets 16.5, 16.6, 16.a)
	
	Organize Composite Annual budget preparation sessions
	Odomase
	Composite Annual Budget prepared
	Composite Annual Budget prepared, Public Hearings organized and Fee Fixing Resolution revised 
	1st July – 31st Dec. 2021
	15,000.00
	-
	-
	CAD
	Other Dept.

	
	
	Organize Composite Annual Action Planning sessions
	Odomase
	Composite Annual Action Plan prepared
	Composite Annual Action Plan prepared 
	1st July – 31st Dec. 2021
	15,000.00
	-
	-
	CAD
	Other Dept.

	
	
	Acquisition of Public Lands
	Entire District 
	
	Public Lands Acquired
	1st January – 31st Dec. 2021
	24,000.00
	-
	-
	CAD
	Other Dept.

	
	
	Construction/ acquisition of Assembly Block
	Odomase
	
	Assembly block acquired
	1st January – 31st Dec. 2021
	250,000.00
	-
	-
	CAD
	Other Dept.

	2.3 Strengthen fiscal decentralization 
	
	
	
	
	
	
	
	
	

	2.3.1 Enhance revenue mobilization capacity and capability of MMDAs (SDG Targets 16.6, 17.1)
	Finance and Revenue Mobilization 
	Implement Revenue improvement Action plan
	Ten Selected communities 
	None
	About 6000 people from 10 settlements sensitized on DA taxes, decent revenue offices with basic logistics and equipment
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	CAD
	Urban/Town/Area Councils, 

	
	
	
	
	
	
	
	
	
	
	
	

	2.3.2 Strengthen PPPs in IGF mobilization (SDG Targets 17.6, 17.17)
	
	Engage a consultant to collect and compile electronic revenue databases for DA
	Odomase 
	None 
	Electronic based revenue database system established 

	1st April – 31st Dec. 2021
	20,000.00
	-
	-
	CAD
	Consultant

	2.5 Improve popular participation  the regional and district levels
	
	
	
	
	
	
	
	
	

	2.5.1 Promote effective stakeholder involvement in development planning process, local democracy and accountability (SDG Target 16.7)
	
	Organize eight (8) town hall and accountability meetings at urban/town/area centres
	Odomase, Chiraa  Nsoatre and Fiapre
	Four town hall meetings organized 
	Eight (8) town hall meetings organized 
	1st January – 31st Dec. 2021
	4,000.00
	-
	-
	CAD, SMAID
	Urban/Town, Area Councils

	6.Human Security and Public Safety
	
	
	
	
	
	
	
	
	
	
	

	6.1 Enhance security service delivery
	
	
	
	
	
	
	
	
	

	6.1.1 Transform security services into a world class security institution with modern infrastructure, including accommodation, health and training infrastructure
	General Administration 
	Support security operations 
	






 

	-
	Number of DISEC meetings organized

Logistics support provided to security operatives
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	SWMA
	GNFS, GIS, GPS,

	
	
	Provide temporary accommodation for district police commander and others 
	-
	-
	Residential apartment rented
	1st January – 31st Dec. 2021
	20,000.00
	-
	-
	SWMA
	GPS

	
	
	Renovation of Fire Service Station at Nsoatre
	Nsoatre
	
	Fire Service Station Constructed
	1st January – 31st Dec. 2021
	
	-
	-
	SWMA
	GNFS

	6.2 Enhance public safety 
	
	
	
	
	
	
	
	
	

	6.2.8 Promote security awareness of the various communities through neighborhood watch schemes (SDG Targets 16.1, 16.7)
	
	Provide technical support for voluntary community watch committees annually
	Entire District
	
	Reduction in crime rate
	1st January – 31st Dec. 2021
	2,000.00
	-
	-
	CAD
	GPS, TCs, U/T/AC

	7.1 Corruption and Economic Crimes
	
	
	
	
	
	
	
	
	
	
	

	7.1 Promote the fight against corruption and economic crimes
	
	
	
	
	
	
	
	
	

	7.1.1 Ensure continued implementation of the National Anti-Corruption Action Plan (NACAP) (SDG Targets 16.5, 16.b.)
	
	Support the implementation of NACAP and ARAP (Accountability, Rule of Law and Anti-Corruption Programme
	Odomase
	
	NACAP and ARAP implemented
	1st January – 31st Dec. 2021
	-
	-
	5,000.00
	NCCE
	SWDA

	12.Culture and National Development
	
	
	
	
	
	
	
	
	
	
	

	12.1.Promote culture in the development process 
	
	
	
	
	
	
	
	
	

	12.1.10 Mainstream culture in all aspect of national development (SDG Targets 4.7, 17.14)
	Administration 
	Construction of community centre at Odomase
	Odomase
	-
	Community centre constructed
	1st January – 31st December 2021
	200,000.00
	-
	-
	SWMA
	TAs

	
	
	Compile information on the cultural sector of the district
	Odomase 
	-
	Inventory of cultural activities compiled 
	1st January – 30th September 2021
	-
	500.00
	-
	CNC
	TCs, SWDA

	
	
	TOTAL=28
	
	
	
	
	
	
	
	
	












SUMMARY OF PLANNED ACTIVITIES UNDER THE DEVELOPMENT DIMENSIONS 

	S/No.
	Development Dimension
	Number of Activities
	Remarks

	
	
	
	

	1.
	Economic Development
	21
	

	2. 
	Social Development
	56
	

	3.
	Environment, Infrastructure and Human Settlement 

	16
	

	4.
	Governance, Corruption and Public Accountability 

	28
	

	
	Total
	121
	




	ACRONYMS
	

	
	

	BRCC
	Brong  Regional Coordinating Council

	CAD
	Central Administration Department

	DSWCD
	Department of Social Welfare and Community Development

	DUR
	Department of Urban Roads

	EPA
	Environmental Protection Agency

	GWCL
	Ghana Water Company

	RDA
	Regional Department of Agriculture

	TAs
	Traditional Authorities





