SUNYANI WEST MUNICIPAL ASSEMBLY

ANNUAL ACTION PLAN FOR 2021

MPCU Secretariat,

Sunyani West Municipal,

Odomase.

September, 2020

SECTION ONE

Table of contents										ii

Declaration											iii

- INTRODUCTION

  - Background of the district						4

  - Scope and focus: Vision and Mission					4

  - Objectives of the Assembly’s Plan					4

SECTION TWO

2.1 Annual Implementation Plan for 2021					5

3.1 summary Sheet									25

3.2 Acronyms 										25

DECLARATION

The Sunyani West Municipal Assembly at a General Assembly meeting held on the …………day of September ……….. Approved the District Annual Action Plan for the period 2021.

SECTION ONE

1.0 INTRODUCTION

## 1.1	Background of the District

The Sunyani West Municipal Assembly (SWMA), which was carved out of Sunyani East District now Sunyani Municipal, is one of the 11 districts in the now Bono Region of the Republic of Ghana. It was established in November 2007 by the Legislative Instrument (LI) 1881 and has moved from District to Municipal status under Local Government Act, 2016 (Act 93) inaugurated on November, 2019 with Odomase as the administrative capital.

## 1.2 Scope and Focus: Vision and Mission

The SWMA’s vision is a future in which all inhabitants will experience enhanced living conditions and adequate socio-economic services of satisfactory quality in a well-maintained, highly decentralized and democratic environment.

The mission of the Assembly is to attain high standards of living for the inhabitants of the district through public-private collaboration, provision of facilities, social services, improved farming and husbandry methods in a sustained environment, and promoting governance through the strengthening of the Municipal Assembly’s (MA) structures.

Our core values are accountability, client-oriented, creativity, diligence, equity, integrity, innovativeness, loyalty, commitment, anonymity, impartiality, permanence, timeliness and transparency.

We also embrace the cultural and ethnic diversity of the Municipality and are committed to promoting good governance, partnership and environmentally sustainable technologies for development actions.

## 1.3 Objectives of the Assembly

In line with the National Medium-Term Development Policy Framework for 2019-2021, the Assembly has adopted the objectives and strategies which are relevant to the achievement of its development aspirations for implementation in its Municipal Medium Term Development Plan for 2019-2021 and Annual Action Plan for 2021.  The goals, objectives, strategies, programmes and sub-programmes are shown in the tables below.

CHAPTER TWO

2.1 Annual Implementation Plan

This section presents the Annual Action Plan for 2021. Specifically, it indicates the various programmes, sub-programmes and their related activities, location, expected outputs, time frame, estimated cost and implementing agencies.

# ANNUAL ACTION PLAN FOR 2021

Development Dimension 1: Economic Development

Goal 1: To build a prosperous society

| Adopted Strategies | Programme/ Sub-programmes | Projects/ Activities | Location | Baseline For 2019 | Output indicators | Time Frame (Quarters) 2020 | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | GoG | IGF | Donor | Lead | Colla. |
| Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Support entrepreneurs and SME development |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 Create an entrepreneurial culture, especially among the youth (SDG Targets 4.4,8.3,8.6) | Economic Development /Trade, Industry and Tourism Services | Support entrepreneurial skill training | Selected project beneficiary communities | No. of youth enterprises established | New trainings conducted for youth enterprises established | 1st January – 30th Sept. 2021 | 30,000.00 | - | 100,000.00 | ACTIOAID/SWMA | NIIT, NVTI |
| 3.4 Enhance Domestic Trade |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.6 Develop modern markets and retail infrastructure in every district to enhance domestic trade (SDG Targets 17.15) | Economic Development /Trade, Industry and Tourism Services | Completion of lockable stores at kwatire | Kwatire, | Traders sell under grass roofed sheds and in the open | Lockable stores completed | 1st January – 30th Sept. 2021 | 25,000.00 | - | - | CAD | PS |
|  |  | Construction of 3No. storey building | Sansama, Fiapre and Chiraa |  |  | 1st January – 30th Sept. 2021 | 100,000.00 |  | 100,00.00 | CAD | Dept. of Agric |
|  |  | Construct animal slaughter slabs at Odomase and Chiraa | Odomase, Chiraa | No slaughtering slabs or slaughter house in the district | Animal slaughter slab completed | 1st January – 30th Sept. 2021 | 50,000.00 | - | - | CAD | Dept. of Agric |
|  |  | Conversion of kobedi market stalls into lockable stores | kobedi | Traders sell under grass roofed sheds and in the open | Lockable stores completed | 1st January – 30th Sept. 2021 | 30,000.00 | - | - | CAD | PS |
|  |  | Completion of lockable stores at Fiapre | Fiapre |  | Lockable stores completed | 1st January – 30th Sept. 2021 | 25,000.00 | - | - | CAD | Dept. of Agric |
|  |  | Construction of 3-Bedroom Staff bungalow at Odomase for Agric Department | Odomase | No accommodation for the department | 3-Bedroom bungalow constucted | 1st January – 31st Dec. 2021 | 240,000.00 |  |  | CAD | Dept. of Agric |
| 4.2 Ensure improved public investment |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.6 Introduce District Chamber of Agriculture, Commerce and Technology (DCACT) with the mandate to promote agribusiness through enhanced interface between private and public sectors at the district level. (SDG Target 16.6) | Agricultural Development | Support to government flagship programmes (PFJ, 1DF, etc.) | Entire Municipality |  | Government Flagship programmes supported | 1st January – 31st Dec. 2021 | 30,000.00 | - | - | Dept. of Agriculture | SWMA, NGOs |
| 4.3 Improve production efficiency and yield |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.3 Reinvigorate extension services (SDG Target 2.a) | Agricultural Development | Train 45 new FBOs and 15 existing FBOs to support extension services | Entire District |  | 45 new FBOs and 15 existing FBOs trained | 1st January – 30th Sept. 2021 | 3,500.00 | - | 4,000.00 | Dept. of Agriculture | Cooperative Unit |
|  |  | Organise District Farmers day celebration |  |  | Farmers day celebrated | 1st December, 2021 | 50,000.00 | - |  | Dept. of Agriculture | SWMA, |
|  | Agricultural Development | Provide agriculture extension services to all farmers | Entire Municipality |  | 30 extension demonstrations on relevant technologies along the value , 40 field days on demonstrations and 2 study tours conducted | 1st January – 31st Dec. 2021 | 18,000.00 | - | 18,000.00 | Dept. of Agriculture | SWMA, NGOs |
|  | Agricultural Development |  |  |  | 3768 home and field visits undertaken yearly to educate farmers and other stakeholders on improved technologies | 1st January – 31st Dec. 2021 | 40,800.00 | - | 40,800.00 | Dept. of Agriculture | SWMA, NGOs |
|  | Agricultural Development |  |  |  | functional two (2) plant clinics in the district | 1st January – 31st Dec. 2021 | 600.00 | - | - | Dept. of Agriculture | SWMA, NGOs |
| 4.3.4 Ensure effective implementation of the yield improvement programme (SDG Targets 2.1, 2.4) | Agricultural Development | Organize training for 200 crop farmers and 150 livestock/poultry farmers yearly on improved technologies and livestock husbandry practices respectively | Entire Municipality |  | At least 200 individual farmers trained yearly on improved technologies trained & post-harvest activities | 1st January – 31st Dec. 2021 | 3,200.00 | 3,200.00 | - | Dept. of Agric. | SWMA, NGOs |
|  | Agricultural Development |  |  |  | At least 150 livestock/poultry farmers trained in good husbandry and management practices and 150 farmers on animal nutrition annually | 1st January – 31st Dec. 2021 | 6,000.00 | - | 6000.00 | Dept. of Agriculture | SWMA, NGOs |
|  | Agricultural Development | Introduce a sustained programme of vaccination for all livestock and poultry | Entire Municipality |  | Number of livestock vaccinated annually against common diseases | 1st January – 31st Dec. 2021 | 4,000.00 | - | 4,000.00 | Dept. of Agriculture | SWMA, NGOs |
|  | Agricultural Development | Carry out and disseminate agriculture statistics, research results and information on weather annually | Entire Municipality |  |  | 1st January – 31st Dec. 2021 | 10,000.00 | - | 10,000.00 |  |  |
|  | Agricultural Development | Provide support services and logistics for the implementation of Dept. of agriculture programmes | Municipality |  | computers, a printer, scanner, modem and pen drives procured | 1st January – 31st Dec. 2021 | 6,100.00 | - | - |  |  |
|  | Agricultural Development |  |  |  | Motor bikes purchased | 1st January – 31st Dec. 2021 | 14,000.00 | - | - |  |  |
|  | Agricultural Development |  |  |  | Internal management and organization functions undertaken | 1st January – 31st Dec. 2021 | 26,400.00 | - | 26, 400.00 | Dept. of Agriculture |  |
|  | Agricultural Development |  |  |  | At least 486 internal monitoring and supervisory visits and 12 inter-departmental monitoring and evaluation visits undertaken yearly | 1st January – 31st Dec. 2021 | 46,000.00 | - | 46,000.00 | Dept. of Agriculture |  |
|  | Agricultural Development |  |  |  | At least 3 zonal planning sessions, monthly review meetings, two technical review sessions and one district RELC planning session organized annually | 1st January – 31st Dec. 2021 | 11,600.00 | - | 11,600.00 | Dept. of Agriculture | SWMA, FBOs |
| 4.4Improve Post-Harvest Management |  |  |  |  |  |  |  |  |  |  |  |
|  | Agricultural Development | Organize trainings for 150 processors on the processing and storage of agriculture produce (cassava, maize and vegetables) annually | Entire District | None | 150 processors staple food processors trained | 1st January – 31st Dec. 2021 | 6,400.00 | - | 6,400.00 | Dept. of Agriculture | SWMA, NGOs |
| 4.4.6. Facilitate the provision of storage infrastructure with a drying system at the district level and a warehouse receipt system (SDG Targets 2.3, 12.1,12.3.12.a) | Agricultural Development | Complete payment for construction of warehouses for maize markets at Nsoatre | Nsoatre |  | Warehouse constructed | 1st January – 31st December 2021 | 200,000.00 | - | - | Dept. of Agriculture | SWMA, |
| 6.1.4 Promote and enforce local tourism and develop available and potential sites to meet internationally acceptable standards (SDG Targets 8.9) | Tourism Development | Identify and document tourism potential | Entire District |  | Tourism potentials identified | 1st January – 31st Dec. 2021 | 2,000.00 |  |  | Centre for National Culture | CAD |
|  |  | TOTAL= 18 |  |  |  |  |  |  |  |  |  |

Development Dimension 2: Social Development

Goal 2: To create opportunities for all

|  |  |  |  |  |  |  | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Adopted Strategies | Programme/ Sub-programmes | Projects/ Activities | Location | Baseline for 2019 | Output indicators | Time Frame | GoG | IGF | Donor | Lead | Colla. |
| 1.1 Enhance inclusive and equitable access to, and participation in quality education at all levels |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.5 Ensure inclusive education for all boys and girls with special needs (SDG Targets 4.1, 4.2, 4.5, 4.a) | Social Services Delivery | Organize sensitization workshops for parents to send their children with special needs to school | Entire Municipality | Identified children with special needs integrated in the education system | Identified children with special needs integrated in the education system | 1st January – 31st Dec. 2021 | 4,000.00 | - | - | GES | GHS, DSWDC |
|  | Social Service Delivery /Education and Youth Development | Provide financial assistance to 50 needy but brilliant boys and girls at post basic educational institutions (vocational/technical, secondary etc.) | Odomase |  | 50 needy but brilliant students provided with financial support | 1st January – 31st Dec. 2021 | 50,000.00 | - | - | GES | SWMA |
|  |  | Support Municipal Education Fund | Entire Municipal |  | Municipal Education Fund | 1st January – 31st Dec. 2021 | 75,741.10 | - | - | GES | SWMA |
| 1.1.6 Popularize and demystify the teaching and learning of science, technology, engineering and mathematics (STEM) and ICT education in basic and secondary education. (SDG Target 4.1) | Education and Youth Development | Organize science, technology, engineering and mathematics (STEM) and ICT Education clinics annually | Odomase |  | Number of boys and girls participated in STEM and ICT | 1st January – 31st Dec. 2021 | 9,000.00 | - | - | GES | SWMA |
|  |  | Providing desktop computers for schools | Entire Municipality |  | Providing desktop computers for schools completed | 1st January – 31st Dec. 2021 | 100,000.00 | - | - | SWDA | GES |
|  |  | Complete payment for Construction of 1No. 3-unit classroom block with ancillary facilities at Abronye Presby Primary | Abronye |  | 1No. 3-unit classroom block with ancillary facilities at Abronye Presby School constructed | 1st January – 31st Dec. 2021 | 10,,472.30 |  |  | SWDA | GES |
|  |  | Construction of 1No. 3-unit KG Block for Notre Dame Girls Model School | Fiapre |  | 1No. 3-unit KG Block for Notre Dame Girls Model School constructed | 1st January – 31st Dec. 2021 | 250,000.00 |  |  | SWDA | GES |
| 1.1.10 Expand infrastructure and facilities at all levels (SDG Target 4.a) | Education and Youth Development | Construction of workshop for Nsoatre Vocational Institute | Nsoatre |  | Workshop contsructed | 1st January – 31st Dec. 2021 | - | - |  | GES | SWMA |
|  |  | Renovation of school buildings | Municipal wide |  |  | 1st January – 31st Dec. 2021 |  |  |  | GES | SWMA |
|  |  | Construction of 1No. 6-Bedroom Teacher’s Bungalow | Adouonya |  |  | 1st January – 31st Dec. 2021 | 340,000.00 | - | . | GES | SWMA |
|  |  | Procurement of 400 PCS Dual Desk for Schools | Municipal Wide |  |  | 1st January – 31st Dec. 2021 | 120,00.00 | - | . | GES | SWMA |
|  |  | Complete payment for construction of 1No.3Units-Classroom block with Ancillary Facilities at Mantukwa | Mantukwa |  | payment for construction of 1No.3Units-Classroom block with Ancillary Facilities at Mantukwa completed | 1st January – 31st Dec. 2021 | 14,872.45 | - | - | GES | SWMA |
|  | Education and Youth Development | Rehabilitate basic schools with dilapidate classroom infrastructure | Chiraa/Nsoatre/ Odomase |  | Selected schools | 1st January – 31st Dec. 2021 | 205,360.95 | - | - | GES | SWMA |
|  |  | Construction of 1No. 3-unit classroom block with ancillary facilities at African Faith Nsoatre | Nsoatre |  | Teaching and learning enhanced | 1st January – 31st Dec. 2021 | 250,000.00 | - | - | GES | SWMA |
|  |  | Construction of 1No. 3-unit classroom block with ancillary facilities at Baamu | Baamu |  | Teaching and learning enhanced | 1st January – 31st Dec. 2021 | 250,000.00 | - | - | GES | SWMA |
|  |  | Construct 1No. 3-unit classroom block with office, store and library for Kantro R/C Block | Kantro |  | 1No. 3-unit classroom block with office, store and library constructed | 1st January – 31st Dec. 2021 | - | - | 400,000.00 | GES | SWMA |
|  |  | Construction of I No. 5-seater toilet for Methodist Primary school | Ayakomaso |  | Toilet Facility Constructed | 1st January – 31st Dec. 2021 | 45,000.00 | - | - | GES | SWMA |
|  |  | Construction of 1No. 3-unit classroom block with ancillary facilities at Fiapre Islamic | Fiapre |  | 1No. 3-unit classroom block with ancillary facilities at Fiapre Islamic constructed | 1st January – 31st Dec. 2021 | 320,000.00 | - | - | GES | SWMA |
|  |  | Supply of furniture to Fiapre Islamic School | Fiapre |  | Supply of furniture to Fiapre Islamic School completed | 1st January – 31st Dec. 2021 | 195,153.00 | - | - | GES | SWMA |
| 1.2.2 Build effective partnership with religious bodies, civic organizations and private sector in delivery of quality education (SDG Target 17.17) |  | Organize DEOC meetings | Odomase |  | DEOC meetings held | 1st January – 31st Dec. 2021 | 1,260.00 | - | - | GES | SWMA |
| 1.2.7 Enhance quality teaching and learning (SDG Targets 4.7, 4.c,) |  | Conduct regular monitoring and supervision of schools | Entire Municipality |  | All basic and secondary schools monitored | 1st January – 31st Dec. 2021 | 5,247.00 | - | - | GES | CAD, SWCD |
| 1.2.8 Ensure adequate supply of teaching and learning materials (SDG Target 4.c) |  | Provide teaching and learning materials for basic schools | Selected Schools |  | TLMs supplied | 1st January – 31st Dec. 2021 | 10,050.00 | - | - | GES | SWMA |
|  | Education and Youth Development | Organize independence Day anniversary | Odomase |  | No. of schools participated in the district celebration | 1st January to 31st March 2021 | 30,000.00 | - | - | DA | DE |
|  |  | Complete the Construction of 1No. 3-unit Teachers Bungalow at Abisu | Abisu |  | Teachers Bungalow completed | 29th October, 2018 – 30th April, 2021 | 121,944.50 |  |  | GES | SWMA |
|  |  | Construction of teachers Bungalow at Adounya | Adounya |  | Teachers Bungalow constructed | 1st January – 31st Dec. 2021 | 121,944.50 |  |  | GES | SWMA |
| 1.2 Strengthen school management systems |  |  |  |  |  |  |  |  |  |  |  |
| Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Ensure affordable, equitable, easily accessible and universal health coverage |  |  |  |  |  |  |  |  |  |  |  |
|  | Health Delivery | Construction of CHPS Compound | Fiapre Zongo |  | CHPS Compound constructed | 1st January – 31st March 2021 | - | - | 180,000.00 | GHS | SWMA |
| 2.1.1 Accelerate implementation of Community based Health Planning and Services (CHPS) policy to ensure equity in access to health care (SDG Targets 1.2, 1.3, 3.1, 3.2, 3.3, 3.8, 16.6) | Health Delivery | Construct 1No. toilet facility for Kantro CHPS compound with nurses quarters | Kantro |  | Toilet and nurses quarters completed | 1st January – 31st March 2021 | - | - | 230,000.00 | GHS | SWMA, Heart for Children’s Foundation |
| 2.1.2 Expand and equip health facilities (SDG Targets 3.8) | Health Delivery | Rehabilitate and construct additional rooms for Dumasua Health Centre | Dumasua |  | Additional rooms -dispensary and laboratory provided | 1st January – 30th December 2021 | 45,000.00 | - | - | GHS | SWMA |
|  |  | Complete payment for Construction of fence wall and concrete walkway at Fiapre Health Centre | Fiapre |  | Fence wall constructed and pavement constructed | 1st January – 30th December 2021 | 100,000.00 | - | - | GHS | SWMA |
|  |  | Support the construction of NHIS office | Odomase |  | NHIS office constructed | 1st January – 30th December 2021 | 6,266.66 | - | - | GHS | SWMA |
|  |  | Furnishing of Health Facilities within the Municipal | Municipal Wide |  | Health Facilities within the Municipal furnished | 1st January – 30th December 2021 | 100,000.00 | - | - | SWMA | GHS |
| 2.3.2 Intensify implementation of malaria control programme (SDG Target 3.3) | Health Delivery | Support malaria prevention education and services | Entire Municipality | Not applicable | Number of participants educated by gender | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | GHS | SWMA |
| 2.4 Ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups |  |  |  |  |  |  |  |  |  |  |  |
| HIV & AIDS |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.3 Intensify behavior change strategies, especially for high-risk groups for HIV and AIDS and TBs (SDG Targets 3.3, 3.7) | Health Delivery | Implement District Response activities on HIV & AIDS | Entire Municipality |  | Number of HIV counselling and testing services conducted | 1st January – 31st Dec. 2021 | 7,862.44 | - | - | GHS | SWMA |
| Population Management |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.7 Improve maternal and adolescent reproductive health (SDG Targets 3.1, 3.7) |  | Support Ghana Health Service to deliver adolescent health services | All Adolescent Corners |  | Increased number of adolescents accessing services from adolescent corners | 1st January – 31st Dec. 2021 | 2,500.00 | - | - | GHS | SWMA |
| Water & Sanitation |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Improve access to safe and reliable water supply services for all |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.7 Undertake tree planting along the banks of all major water bodies and their tributaries to reduce silting and pollution from human activities | Water bodies management | Support CBO initiated tree planting campaigns along major river bodies and around school buildings | Selected communities |  | Trees planted along major river bodies and school buildings | 1st January – 31st Dec. 2021 | 1,500.00 | - | - | Forest Services Division | SWMA, NADMO, CBOs |
| 5.1.2 Ensure sustainable financing of operations and maintenance of water supply systems (SDG Target 17.3) | Water and Sanitation | Maintenance of existing boreholes | Entire Municipality |  | Broken down boreholes maintained | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | MWD/DWST | CWSA |
| 5.1.3 Provide mechanized borehole and small town water systems (SDG Target 6.1) | Water and Sanitation | Support community mobilization and drilling/construction of 20 potable water systems (boreholes fitted with pumps and piped systems) | Entire Municipality |  | Supported the construction of 20 boreholes with hand pumps | 1st January – 31st Dec. 2020 | 38,250.00 | - | - | MWD/DWST | CWSA |
|  |  | Construction and drilling of 8No. boreholes with fitted hand pumps | Notre Dame shs Chiraa–Oti Yeboah Canada SAHES Kantro No.1 Boliso –Nsoatre Beposo-Abisu Afrasu No.2 |  | Construction and drilling of 8No. boreholes with fitted hand pumps completed | 1st January – 31st Dec. 2021 | 100,000.00 | - | - | MWD/DWST | CAD |
|  |  | Drilling of 3No. Boreholes and Mechanization of 1 existing borehole with hand pump | Kessabente Timbernkwanta , Aduonya Apprakukrom |  | 3No. Boreholes and of 1 existing borehole with hand pump drilled and maintained | 1st January – 31st Dec. 2020 | 30/567.77 | - | - | MWD/DWST | CWSA |
|  |  | Drilling and Construction of 10No. Boreholes with Hand Pump | Abisu Nkranketewaa Kantro No.2 Kantro No.2 Yawsankro Fawoman Appiakrom Nsamsam City Attakrom Tailokrom |  | Drilling and Construction of 10No. Boreholes with Hand Pump completed | 1st January – 31st Dec. 2020 | 257,000.00 | - | - | MWD/DWST | CWSA |
| Social Services Delivery | Water and Sanitation | Rehabilitate 20 potable water supply systems | Entire Municipality |  | 20 water facilities rehabilitated | 1st January – 31st Dec. 2020 | 108,000.00 | - | - | MWD/DWST | Area Mechanics, Contractors |
|  |  | Support the operations of the MWST | Entire District |  | Regular monitoring of water facilities | 1st January – 31st Dec. 2020 | 10,000.00 | - | - | MWD/MWST | CAD |
| Environmental Sanitation and Hygiene |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 Enhance access to improved and reliable environmental sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.2 Create space for private sector participation in the provision of sanitation services (SDG Target 17.17) | Environmental Health and Sanitation Management | Partner private sector companies/individuals to provide modern public toilets in major towns | Odomase, Nsoatre, Chiraa, Dumasua and Fiapre, |  | Improved sanitation services and clean environment | 1st January – 31st Dec. 2021 | 55,000.00 | - | - | CAD-MEHSU | Private Sector Investors, SWMA |
| 5.2.4 Promote National Total Sanitation Campaign (SDG Target 6.2) | Environmental Health and Sanitation Management | Conduct environmental sensitization campaigns | Entire Municipality |  | Number of communities sensitized | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | MEHSU | ISD |
|  | Environmental Health and Sanitation Management | Evacuate/level refuse heaps in major settlements | Chiraa, Nsoatre Fiapre and Odomase |  | Refuse heaps evacuated | 1st January – 31st Dec. 2021 | 100,000.00 | - | - | CAD-EHSU | Private Sector Organization |
|  | Environmental Health and Sanitation Management | Procure sanitation tools and facilities for cleaning and general services | Entire Municipality |  | Brooms, detergents, rakes, litter bins supplied | 1st January – 31st Dec. 2021 | 100,000.00 | - |  | EHSU | CAD |
|  |  | Construction of 1No. 2-seater toilet and urinal at Fiapre Durbar Grounds | Fiapre |  | Toilet and Urinal completed | 1st January – 31st Dec. 2021 | 20,000.00 | - |  | EHSU | CAD |
| Poverty and inequality |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.Eradicate poverty in all its forms and dimension |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Empower the vulnerable to access basic necessities of life (SDG Target 1.4) | Social Services Delivery | Organize sensitization campaigns on social issues for vulnerable groups | Entire Municipality |  | Knowledge impacted | 1st January – 31st Dec. 2021 | 1,000.00 | - | - | MSCD | UTAC, TAs, CBOs |
| Child and Family Welfare |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Ensure effective child protection and family welfare system |  |  |  |  |  |  |  |  |  |  |  |
| 7.1.10 Increase awareness on child protection laws and policies (SDG Targets 5.3, 16.2, 16.3) | Social Welfare and Community Development | Educate the public and enforce child protection laws and policies | Entire Municipality | Number of education campaigns organized Number of cases resolved | Public educated on child protection laws | 1st January – 31st Dec. 2021 | 300.00 | - | - | MSWCD | SWMA, UTACs |
| 7.2.2 Enhance inclusion of children with disability and special needs in all spheres of child development (SDG Targets 4.5, 4.a, 10.2, 11.2) |  | Identify, register and link children with disability and special needs to the relevant institutions for integration or support | Entire Municipality |  | Disabled children identified and supported | 1st January – 31st Dec. 2021 | 600.00 | - | - | MSWCD | CAD, DOVVSU, CHRAJ |
|  |  | Undertake Gender based activities | Entire Municipality |  |  |  |  |  |  |  |  |
| 7.2.6 Eliminate the worst forms of child labour by enforcing laws on child labour and child protection (SDG Targets 5.3, 16.2, 16.3) |  | Support the establishment of relevant structures (child panels etc.) to promote justice for children, | Entire Municipality |  | Relevant child protection structures established | 1st January – 31st Dec. 2021 | 100.00 | - | - | MSWCD | CAD, DOVVSU, CHRAJ |
| Gender Equality |  |  |  |  |  |  |  |  |  |  |  |
| 9.2 Promote economic empowerment of women |  |  |  |  |  |  |  |  |  |  |  |
| 9.2.5 Improve access to education, health and skills training in income generating activities for vulnerable persons including head potters (SDG Targets 3.8, 4.5) | Social Welfare and Community Development | Support the organization of skills training for target groups and unemployed women | Entire Municipality |  | Skills training organised for target and unemployed women groups | 1st January – 31st Dec. 2021 | 1,000.00 | - | - | MSWCD | SWMA, UTACs |
|  |  | Organize adult education programmes/mass meetings on issues affecting children and domestic violence. | Entire Municipality |  | 72 groups trained on child related issues and domestic violence | 1st January – 31st Dec. 2021 | 300.00 | - | - | MSWCD | CAD, DOVVSU, CHRAJ |
| Social Protection |  |  |  |  |  |  |  |  |  |  |  |
| 10.1 Strengthen social protection especially for children women persons with disabilities and the elderly |  |  |  |  |  |  |  |  |  |  |  |
| 10.1.3 Strengthen and effectively implement existing social protection intervention programmes and expand their coverage to include all vulnerable groups (SDG Targets 1.3, 5.4, 10.4) | Social Welfare and Community Development | Support the implementation of livelihood Empowerment Against Poverty Programme | Entire Municipality |  | Number of beneficiaries | 1st January – 31st Dec. 2021 | 1000.00 | - | - | MSWCD | CAD |
| Social Services Delivery | Social Welfare and Community Development | Conduct inspection visits to early childhood development centres | Odomase, Fiapre Nsoatre, Chiraa circuits |  | 12 public and private early childhood development centres inspected | 1st January – 31st Dec. 2021 | 340.00 | - | - | MSWCD | CAD |
| Social Services Delivery | Social Welfare and Community Development | Mediate and provide counselling on child and family welfare conflicts/issues to clients | Odomase |  | Type and Number of conflicts resolved | 1st January – 31st Dec. 2021 | 300.00 | - | - | MSWCD | CAD |
| Gender Equality |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organize livelihood skills training for women | Odomase, Dumasua, Koduakrom Chiraa, Fiapre and Nsoatre |  | 20 women groups provided with livelihood skills | 1st January – 31st Dec. 2021 | - | - | - | DSWCD | CAD |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |
| 11.1 Promote full participation of PWDs in social and economic development of the country |  |  |  |  |  |  |  |  |  |  |  |
| 11.1.5 Ensure effective implementation of the three (3) percent increase in DACF disbursements to PWDs (SDG Targets 16.6) |  | Facilitate and Manage the disbursement of Disability fund | Entire Municipality |  | Implement PWD action plan Enhanced economic and social wellbeing of PWDs | 1st January – 31st Dec. 2021 | 64,787.00 | - | - | SWMA | PWDs, |
| 11.3.1 Ensure the implementation of Ghana Accessibility standards to ensure access of PWDs to the built environment, goods, services and assistive devices (SDG Targets 10.2, 11.1) | Social Welfare and Community Development | Facilitate the provision of walkways in newly constructed public buildings | Entire Municipality |  | 80 percent of activities implemented | 1st January – 31st Dec. 2021 | - | 500.00 | - | SWMA | Association of PWDs |
| 14.1.8 Promote less recognized sporting activities (SDG 1.a, 17.3) | Social Services Delivery | Support sporting activities (e.g. table tennis and football) for basic schools and communities | Entire Municipality |  | Sports enhanced | 1st January – 30th June 2021 | 5,000 |  |  | SWMA | YEA |
|  |  | TOTAL=61 |  |  |  |  |  |  |  |  |  |

Development Dimension 3: Environment, Infrastructure and Human Settlement

Goal 3: Safeguard the natural environment and ensure a resilient built environment

|  |  |  |  |  |  | Time Frame (Quarters) | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programmes | Sub-programmes | Projects/ Activities | Location | Baseline for 2017 | Output indicators |  | GoG | IGF | Donor | Lead | Colla. |
| Protected Areas |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Protect forest reserves |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 Support the protection of the remaining network of natural forest and biodiversity hotspots in the country (SDG Targets 6.6, 11.4, 12.2, 15.1, 15.5, 15.9, 15.a, 16.b) | Natural Resources Conservation | Establish checkpoints to control illegal lumbering in forest reserves and government plantations | Entire Municipal | None | Check points to control illegal logging of lumber established | 1st January – 30th June 2021 | - | 2,000.00 | - | CAD | PS |
| Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Enhance climate change and resilience |  |  |  |  |  |  |  |  |  |  |  |
| 7.1.10 Mainstream climate change in national development planning and budgeting processes (SDG Targets 11.b, 13.2) | Environmental and Sanitation Management | Implement climate change related risk reduction, mitigation and adaptation actions | Entire Municipal |  | climate change related risk reduction, mitigation and adaptation actions implemented | 1st January – 31st December 2021 | 20,000.00 | - | - | NADMO | EPA, GMeT |
| Disaster Management |  |  |  |  |  |  |  |  |  |  |  |
| 8.1 Promote proactive planning for disaster prevention and mitigation |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Planting of trees in communities affected by sand wining activities | Chiraa Ahyiamu, Tanonom, Canada |  | Planting of trees in communities affected by sand wining activities implemented | 1st January – 31st December 2020 | 15,000.00 | - | - | NADMO | SWDA-CAD |
| 8.1.1 Educate public and private institutions on natural and man-made hazards and disaster risks (SDG Targets 3.d, 13.3.) | Disaster Prevention and Management | Organize education campaigns on bushfires and associated loss of property and danger to the environment | Entire Municipal | Number of communities visited | Number of communities educated | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | NADMO | SWMA-CAD |
| 8.1.2 Strengthen early warning and response mechanism on disasters (SDG Targets 3.d, 13.3.) | Disaster Prevention and Management | Undertake regular removal of silt and refuse from storm drains and culverts | Entire Municipal | Number of communities benefitted from the exercise | Silt removed from storm drains and gutters | 1st January – 31st Dec. 2021 | 25,000.00 | -.;’ | - | NADMO | CAD, GNFS |
|  | Disaster Prevention and Management | Provide relief items to disaster victims | Entire Municipal | No. of relief items distributed | Number of relief items distributed | 1st January – 31st Dec. 2010 | 20,000.00 | - | - | NADMO | CAD, GNFS |
| Transport Infrastructure –Road |  |  |  |  |  |  |  |  |  |  |  |
| 8.1Improve efficiency and effectiveness of road transport infrastructure and services |  |  |  |  |  |  |  |  |  |  |  |
| 8.1.2 Expand and maintain the national road network (SDG Target 9.1, 11.2) | Infrastructure Development | Re-shaping and maintenance of access roads | Entire Municipal | Access roads undergo routine maintenance | 3No. culverts constructed and approaches filled. | 1st January – 31st Dec. 2021 | - | - | 150,000.00 | DFR | SWMA |
| Information Communication Technology |  |  |  |  |  |  |  |  |  |  |  |
| 10.1 Enhance application of ICT in national development |  |  |  |  |  |  |  |  |  |  |  |
| 10.1.2 Mainstream ICT in public sector operations (SDG Target 17.8) |  | Reactivate website and social media platforms | Odmase | Internet connection available | Website reactivated | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | SWMA | MTN |
| Energy and Petroleum |  |  |  |  |  |  |  |  |  |  |  |
| 12.2 Ensure efficient transmission and distribution system |  |  |  |  |  |  |  |  |  |  |  |
| 12.2.4 Revise self-help –electricity project and use means-testing approaches to enable the poor to connect to the national grid (SDG Target 7.b) |  | Support the extension of electricity to unserved areas, street light and purchase of light poles | Entire Municipal | Increased access to electricity in the district | Electricity extended to unserved areas of the district | 1st January – 31st Dec. 2021 | 75,000.00 | - | - | SWMA | VRA, TAs, UTAC |
|  |  | Extension of electricity to Health Centres | Entire Municipal | Connect all Health centres to electricity | Extension of electricity to Health Centres completed | 1st January – 31st Dec. 2021 | 500,000.00 | - | - | SWMA | VRA, TAs, UTAC |
| 13.Drainage and flood control |  |  |  |  |  |  |  |  |  |  |  |
| 13.1 Address recurrent devastating floods |  |  |  |  |  |  |  |  |  |  |  |
| 13.1.3 Intensify public education on indiscriminate disposal of waste (SDG Target 11.6) |  | Organize regular campaigns for cleaning and removal of silt and waste from drains | Entire District | Reduction of floods in major towns | Campaigns for clearing and silt removal organised | 1st January – 31st Dec. 2021 | 11,000.00 |  |  | NADMO | SWMA |
| 14. Infrastructure maintenance |  |  |  |  |  |  |  |  |  |  |  |
| 14.1.3 Establish timely and effective preventive maintenance plan for all public infrastructure (SDG Target 9.a) |  | Rehabilitate /Maintain, Refurbish and Upgrade public infrastructure | Nsoatre, Chiraa and Dumasua | - | No. of streetlights, classroom blocks, health facilities, court buildings maintained | 1st January – 31st Dec. 2021 | 150,000.00 | - | - | SWMA | VRA, UTAC |
| Human Settlement and Housing |  |  |  |  |  |  |  |  |  |  |  |
| 17.1 Promote sustainable, spatially integrated, balanced and orderly development of human settlements |  |  |  |  |  |  |  |  |  |  |  |
| 17.1.1 Fully implement Land Use and Spatial Planning Act 2016 (Act 925) (SDG Targets 16.6, 17.16) | Physical and Spatial Planning | Organize quarterly spatial planning and technical committee meetings | Odomase | Five (5) physical planning meeting organized | Six (6) statutory planning and technical committee meetings held, Number of development applications approved | 1st January – 31st Dec. 2021 | - | 5,000.00 | - | DPP | TAs, Other government |
| Infrastructure delivery and management | Physical and Spatial Planning | Organize physical planning education for stakeholders | Entire District | Five (5) physical planning education campaigns organized for stakeholders | 10 communities sensitized on physical planning procedures | 1st January – 31st Dec. 2021 | - | 8,500.00 | - | DPP | TAs, Other government |
| Infrastructure delivery and management | Physical and Spatial Planning | Provide technical support services to TAs |  |  | Improved service delivery | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | DPP | TAs, Other Government Agencies |
|  |  | Procure office machines, materials and equipment for administrative and field work | Odomase |  | Procure office machines (two computers, A3 scanner, printer and two GPS), planning materials (satellite images etc) and field equipment (two motorbikes) | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | CAD | SWMA |
| Urban Development |  |  |  |  |  |  |  |  |  |  |  |
| 19.1 Promote resilient urban development |  |  |  |  |  |  |  |  |  |  |  |
| 19.1.8 Support implementation of the National Urban Policy and Action Plan and the United Nation’s New Urban Agenda adopted at Habitat III (SDG Targets 11.3,11.a, 11.b) | “ | Support the implementation of street naming and property addressing exercises/Ghana Post digital addressing system | Odomase and Fiapre | Five (5) streets named and all properties address | Five (5) streets named and all properties address | 1st January – 31st Dec. 2021 | 50,000.00 | - | - | DPP | TAs, Other government |
|  |  | TOTAL=16 |  |  |  |  |  |  |  |  |  |

Development Dimension 4: Governance, Corruption and Public Accountability

Goal 4: To maintain a stable, united and safe society

|  |  |  |  |  |  |  | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programmes | Programme /Sub-programmes | Projects/ Activities | Location | Baseline for 2019 | Output indicators | Time Frame | GoG | IGF | Donor | Lead | Colla. |
| 2.1 Deepen political and administrative decentralization |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 Institute mechanism for effective inter-service/inter-sectoral collaboration and cooperation at district, regional and national levels (SDG Targets 16.6, 16.7) | Management and Administration /General Administration | Organize statutory political meetings | Odomase | Three GA ordinary, executive and sub-committee meetings held | Three GA Ordinary meetings, executive committee and sub-committee meetings organized | 1st January – 31st Dec. 2021 | - | 25,000.00 | - | MA | Government Agencies |
|  |  | Organize statutory management meetings | Odomase |  | At least four management meetings organized | 1st January – 31st Dec. 2021 | - | 1,500.00 | - | CAD | Depts of the Assembly |
|  |  | Undertake landscaping, paving and construction of summer hut for DCE’s residence | Odomase |  | Landscaping completed | 1st January – 31st Dec. 2021 | - | 71,324.24 | - | SWMA | PSO |
|  |  | Furnishing of Assembly Block | Odomase |  | Furnishing of Assembly Block completed | 1st January – 31st Dec. 2021 | 50,000.0 | - | - | CAD | SWMA |
|  |  | Rehabilitation of DCE’s residence | Odomase |  | Roofing changed | 1st January – 31st Dec. 2021 | - | 85,000.00 | - | CAD | SWMA |
|  |  | Complete payment for construction of 1N0.3-Units Semi-ditch staff quarters at Odomase | Odomase |  | payment for construction of 1N0.3-Units Semi-ditch staff quarters at Odomase completed | 1st January – 31st Dec. 2021 | 32,039.22 | - | - | CAD | SWMA |
| 2.1.5 Strengthen the capacity of the ILGS to deliver on its mandates |  | Organize training for Assembly members and staff on the LGA | Odomase | None | 54 Assembly members and 24 staff trained | 1st April – 31st Dec. 2021 | 20,000.00 | - | 30,000.00 | CAD | Consultants |
| 2.1.7 Strengthen sub-district structures (SDG Targets 16.6, 17.9) | General Administration | Complete the Construction of an office building for Fiapre Town council | Fiapre | None | Fiapre town council office completed | 1st January – 31st Dec. 2021 | 158,576.50 | - | - | CAD | PS |
|  |  | Provide temporary offices for Koduakrom and Dumasua Area Councils | Koduakrom and Dumasua |  | Temporary offices provided | 1st January – 31st Dec. 2021 | 11,449.78 | - | - | CAD | SWMA |
|  |  | Procurement of 2No.Motobycycles for official duties | Odomase |  | 2No.Motobycycles for official duties procured | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | CAD | SWMA |
|  |  | Support the establishment of sub-structures within the Municipality | Entire Municipal |  | sub-structures established | 1st January – 31st Dec. 2021 | 75,741.00 | - | - | CAD | SWMA |
|  |  | Provide support services and logistics to the urban/town/area councils | Awua –Domase, Odomase No.1, Fiapre, Nsoatre, Koduakrom and Chiraa | None | Office furniture, stationery etc | 1st January – 31st Dec. 2021 | 60,000.00 | - | - | CAD | Private Sector |
|  |  | Complete payment for construction of District Police Station | Odomase |  | District Police Station constructed | 1st January – 31st Dec. 2021 | 17,726.16 | - | - | CAD | SWMA |
|  |  | Organize refresher training for 28 unit committees on their mandate and functions | Selected electoral areas | None | 28 unit committees trained | 1st January – 31st Dec. 2021 | 1,860.00 | - | - | DSWCD | NGOs, Urban/Town/Area Council |
| 2.2 Improve decentralized planning through Municipal enumeration |  | Undertake the creation of administrative database | Entire Municipality | - | Administrative database created | 1st January – 31st December 2021 | 2,400.00 | - | - | STATS | All Departments |
|  |  | Undertake monthly market readings on selected items for the various markets | Entire Municipality | - | Computation of Monthly CPI and inflation rates | 1st January – 31st December 2021 | 2,400.00 |  |  | STATS | GSS |
| 2.2.1 Strengthen local level capacity for participatory planning and budgeting (SDG Targets 16.6, 16.7.) | Planning, Budgeting and Coordination | Coordinate planning and budgeting activities of the Assembly | Odomase | Four quarterly DPCU meetings organized | Four (4) DPCU meetings organized | 1st January – 31st Dec. 2021 | 6,000.00 | - | - | CAD | SWMA |
|  |  | Organization of Audit Committee meetings | Odomase |  | Four (4) Audit committee meeting organized | 1st January – 31st Dec. 2021 | 10,000.00 | - | - | CAD | SWMA |
|  |  | Conduct AAP implementation monitoring and evaluation. | Odomase | Jointly organized with DPCU meetings | Four (4) quarterly review meetings jointly organized with DPCU meetings | 1st January – 31st Dec. 2021 | 2,000.00 |  | - | CAD | Depts. of the Assembly |
|  |  | Organize refresher training for staff of DA and Area Council members | Odomase | None | Two refresher training organized for heads of department of the Assembly | 1st April – 30th June 2021 | 10,000.00 |  | - | CAD | Urban/Town/Area Councils |
| 2.2.4 Ensure implementation of planning and budgeting provisions in LI 2232 and the Public Financial Management Act, 2016 (Act 921) (SDG Targets 16.5, 16.6, 16.a) |  | Organize composite annual budget preparation sessions | Odomase | Composite Annual Budget prepared | Composite Annual Budget prepared, Public Hearings organized and Fee Fixing Resolution revised | 1st July – 31st Dec. 2021 | 15,000.00 | - | - | CAD | Other Dept. |
|  |  | Organize composite annual action planning sessions | Odomase | Composite Annual Action Plan prepared | Composite Annual Action Plan prepared | 1st July – 31st Dec. 2021 | 15,000.00 | - | - | CAD | Other Dept. |
|  |  | Acquisition of Public Lands | Entire District |  | Public Lands Acquired | 1st January – 31st Dec. 2021 | 24,000.00 | - | - | CAD | Other Dept. |
|  |  | Construction/ acquisition of Assembly Block | Odomase |  | Assembly block acquired | 1st January – 31st Dec. 2021 | 250,000.00 | - | - | CAD | Other Dept. |
| 2.3 Strengthen fiscal decentralization |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 Enhance revenue mobilization capacity and capability of MMDAs (SDG Targets 16.6, 17.1) | Finance and Revenue Mobilization | Implement revenue improvement action plan | Ten Selected communities | None | About 6000 people from 10 settlements sensitized on DA taxes, decent revenue offices with basic logistics and equipment | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | CAD | Urban/Town/Area Councils, |
| 2.3.2 Strengthen PPPs in IGF mobilization (SDG Targets 17.6, 17.17) |  | Engage a consultant to collect and compile electronic revenue databases for DA | Odomase | None | Electronic based revenue database system established | 1st April – 31st Dec. 2021 | 20,000.00 | - | - | CAD | Consultant |
| 2.5 Improve popular participation the regional and district levels |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 Promote effective stakeholder involvement in development planning process, local democracy and accountability (SDG Target 16.7) |  | Organize eight (8) town hall and accountability meetings at urban/town/area centres | Odomase, Chiraa Nsoatre and Fiapre | Four town hall meetings organized | Eight (8) town hall meetings organized | 1st January – 31st Dec. 2021 | 4,000.00 | - | - | CAD, SMAID | Urban/Town, Area Councils |
| 6.Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Enhance security service delivery |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.1 Transform security services into a world class security institution with modern infrastructure, including accommodation, health and training infrastructure | General Administration | Support security operations |  | - | Number of DISEC meetings organized Logistics support provided to security operatives | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | SWMA | GNFS, GIS, GPS, |
|  |  | Provide temporary accommodation for district police commander and others | - | - | Residential apartment rented | 1st January – 31st Dec. 2021 | 20,000.00 | - | - | SWMA | GPS |
|  |  | Renovation of Fire Service Station at Nsoatre | Nsoatre |  | Fire Service Station Constructed | 1st January – 31st Dec. 2021 |  | - | - | SWMA | GNFS |
| 6.2 Enhance public safety |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.8 Promote security awareness of the various communities through neighborhood watch schemes (SDG Targets 16.1, 16.7) |  | Provide technical support for voluntary community watch committees annually | Entire District |  | Reduction in crime rate | 1st January – 31st Dec. 2021 | 2,000.00 | - | - | CAD | GPS, TCs, U/T/AC |
| 7.1 Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Promote the fight against corruption and economic crimes |  |  |  |  |  |  |  |  |  |  |  |
| 7.1.1 Ensure continued implementation of the National Anti-Corruption Action Plan (NACAP) (SDG Targets 16.5, 16.b.) |  | Support the implementation of NACAP and ARAP (Accountability, Rule of Law and Anti-Corruption Programme | Odomase |  | NACAP and ARAP implemented | 1st January – 31st Dec. 2021 | - | - | 5,000.00 | NCCE | SWDA |
| 12.Culture and National Development |  |  |  |  |  |  |  |  |  |  |  |
| 12.1.Promote culture in the development process |  |  |  |  |  |  |  |  |  |  |  |
| 12.1.10 Mainstream culture in all aspect of national development (SDG Targets 4.7, 17.14) | Administration | Construction of community centre at Odomase | Odomase | - | Community centre constructed | 1st January – 31st December 2021 | 200,000.00 | - | - | SWMA | TAs |
|  |  | Compile information on the cultural sector of the district | Odomase | - | Inventory of cultural activities compiled | 1st January – 30th September 2021 | - | 500.00 | - | CNC | TCs, SWDA |
|  |  | TOTAL=28 |  |  |  |  |  |  |  |  |  |

SUMMARY OF PLANNED ACTIVITIES UNDER THE DEVELOPMENT DIMENSIONS

| S/No. | Development Dimension | Number of Activities | Remarks |
| --- | --- | --- | --- |
| 1. | Economic Development | 21 |  |
| 2. | Social Development | 56 |  |
| 3. | Environment, Infrastructure and Human Settlement | 16 |  |
| 4. | Governance, Corruption and Public Accountability | 28 |  |
|  | Total | 121 |  |

| ACRONYMS |  |
| --- | --- |
| BRCC | Brong Regional Coordinating Council |
| CAD | Central Administration Department |
| DSWCD | Department of Social Welfare and Community Development |
| DUR | Department of Urban Roads |
| EPA | Environmental Protection Agency |
| GWCL | Ghana Water Company |
| RDA | Regional Department of Agriculture |
| TAs | Traditional Authorities |